## WBS
Project | Udacity JAVA OOP |  |  | Writer of this sheet | Korn | Created at | 2024-08-26 | Finished
[6 empty] | Updated at | 2024-09-12 | Working on | 2024-08-26
No. | Work | Schedule(date) |  | Actual days you took |  | Man-hours（hour） |  | Progress | Note
|  | Start | End | Start | End | Plan | Actual result
Object Oriented Programming in Java
1 | Chapter 1 The World of Objects | 2024-08-26 | 2024-08-29 | 2024-08-26 | 08/28/24 | 16 | 10 | 100%
| Section 1.1 – 1.5 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 4 | 2 | 100%
| Section 1.6 – 1.10 | 8/27/2024 | 8/27/2024 | 2024-08-26 | 8/27/2024 | 4 | 2 | 100%
| Section 1.11 – 1.15 | 8/28/2024 | 8/28/2024 | 8/27/2024 | 8/27/2024 | 4 | 3 | 100%
| Section 1.16 – 1.21 | 8/29/2024 | 8/29/2024 | 8/27/2024 | 8/28/2024 | 4 | 3 | 100%
2 | Chapter 2 User Interaction | 2024-08-30 | 2024-09-04 | 2024-08-28 | 2024-08-29 | 8 | 7 | 100%
| Section 2.1 – 2.6 | 2024-08-30 | 2024-09-02 | 2024-08-28 | 2024-08-29 | 4 | 3 | 100%
| Section 2.7 – 2.13 | 2024-09-03 | 2024-09-04 | 2024-08-29 | 2024-08-29 | 4 | 4 | 100%
3 | Chapter 3 Project 1: Guess The Movie | 2024-09-05 | 13/5/2024 | 2024-08-29 | 2024-08-30 | 32 | 18 | 100%
| Section 3.1 : Introduction | 2024-09-05 | 2024-09-10 | 2024-08-29 | 2024-08-30 | 16 | 10 | 100%
| Section 3.2 : Hints | 2024-09-11 | 2024-09-13 | 2024-08-29 | 2024-08-30 | 16 | 8 | 100%
4 | Inheritance | 2024-09-16 | 2024-09-19 | 2024-09-02 | 2024-09-04 | 18 | 13 | 100%
| Section 4.1 – 4.6 | 2024-09-16 | 2024-09-16 | 2024-09-02 | 2024-09-02 | 6 | 3 | 100%
| Section 4.7 – 4.12 | 2024-09-17 | 2024-09-17 | 2024-09-03 | 2024-09-03 | 6 | 5 | 100%
| Section 4.13 – 4.19 | 2024-09-18 | 2024-09-19 | 2024-09-04 | 2024-09-04 | 6 | 5 | 100%
5 | Collections | 2024-09-20 | 2024-09-25 | 2024-09-04 | 2024-09-06 | 12 | 10 | 100%
| Section 5.1 – 5.4 | 2024-09-20 | 2024-09-21 | 2024-09-04 | 2024-09-05 | 4 | 3 | 100%
| Section 5.5 – 5.8 | 2024-09-22 | 2024-09-23 | 2024-09-05 | 2024-09-06 | 4 | 4 | 100%
| Section 5.9 – 5.11 | 2024-09-24 | 2024-09-25 | 2024-09-06 | 2024-09-06 | 4 | 3 | 100%
6 | Project 2: Space Challenge | 2024-09-26 | 2024-10-08 | 2024-09-09 | 2024-09-12 | 32 | 26 | 100%
| Section 6.1 : Introduction | 2024-09-26 | 2024-10-03 | 2024-09-09 | 2024-09-12 | 16 | 14 | 100%
| Section 6.2 : Mission specs | 2024-10-04 | 2024-10-08 | 2024-09-09 | 2024-09-12 | 16 | 12 | 100%

## How to write in WBS
Project | Training |  |  | Writer of this sheet |  | Created at |  | Finished
[6 empty] | Updated at |  | Working on
No. | Work | Schedule(date) |  | Actual days you took |  | Man-hours（hour） |  | Progress | Note
|  | Start | End | Start | End | Plan | Actual result
0 | Learn how to write code
0.1 | Writing Client side Code
0.1.1 | Write code of conditional branching process without sample. | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 12 | 12 | 100%
0.1.2 | Write code of looping process without sample.
0.2 | Learn server side code by explaining code
0.2.1 | Explain OrderController.java with comment
0.2.2 | Explain OrderService.java with comment.
0.2.3 | Explain OrderRepository.java with comment.
0.2.4 | Explain OrderDatasource.java with comment.
0.2.5 | Explain ExampleOrderRequest.java with comment.
0.2.6 | Explain ExampleOrder.java with comment.
0.3 | Writing server side code
0.3.1 | Download template from SpringInitializr. Do it as same as you did in a development of Todo Application.
0.3.2 | Create new datatable into your database which you had created on MySQL of CentOS. Do it as same as you did in a development of Todo Application.
0.3.3 | Write Cotroller.java
0.3.4 | Write Request.java
0.3.5 | Write Model.java
0.3.6 | Write Service.java
0.3.7 | Write Repository.java
0.3.8 | Write Datasource.java
0.3.9 | Write ValidateResult.java
Write your name in here.
Write date that you started to get on any work and date that you finished the work in here
Write time that you took to finish you work in here.
Write how much work progressed ny percentage in here.